## Sheet1
SPRINT - Hour Breakdown
TASKS | Est. Hours | Wed Hours | Thur Hours | Fri Hours | Sat Hours | Sun Hours | Mon Hours | Tue Hours | Total Hours
Search Bar | 6 | 1 | 2 | 1 |  | 1 |  | 1 | 6
List of properties | 4 |  | 1 | 2 |  |  |  |  | 3
Selection Box | 6 |  | 1 | 2 | 1 | 2 |  | 1 | 7
List of properties | 4 |  |  | 2 | 2 |  |  |  | 4
Selection Box | 6 | 1 | 1 | 1 |  |  |  | 3 | 6
List of properties | 4 |  |  | 1 | 1 | 2 | 1 |  | 5
Selection Box | 6 | 1 |  |  | 3 | 1 | 2 |  | 7
List of properties | 4 |  | 1 | 1 | 1 | 1 |  |  | 4
Selection Box | 6 | 1 | 2 | 1 |  | 1 |  | 1 | 6
List of properties | 4 |  | 1 | 2 |  |  |  |  | 3
Selection Box | 6 |  | 1 | 2 | 1 | 2 |  | 1 | 7
List of properties | 4 |  |  | 2 | 2 |  |  |  | 4
Selection Box | 6 | 1 | 1 | 1 |  |  |  | 3 | 6
List of properties | 4 |  |  | 1 | 1 | 2 | 1 |  | 5
Form Submission | 6 | 1 |  |  | 3 | 1 | 2 |  | 7
Username creation | 1 |  | 1 | [5 empty] | 1
Link information to database | 3 |  | 1 | 1 | 1 |  |  |  | 3
Submit form | 6 |  | 1 | 2 | 3 |  |  |  | 6
Log in | 4 |  | 1 | 2 | 1 | 1 |  |  | 5
Click button to log out | 1 |  |  | 1 |  |  |  |  | 1
Update edited information to database | 4 |  | 1 | 1 | 1 | 1 |  |  | 4
Password storage in database | 6 |  | 2 | 2 | 2 |  |  |  | 6
Incorrect password message | 4 |  | 1 | 2 |  |  |  |  | 3
Actual Burndown | 160 | 6 | 19 | 30 | 23 | 15 | 6 | 10 | 160
Estimated Burndown | 160 | 10 | 20 | 10 | 20 | 20 | 20 | 5 | 160